## Slide 1: Arrakis Realty Tech Systems at a glance
Pre-start
Setup & approvals · Prior to Work
Phase 0
Launch · Weeks 1–2
Phase 1
Full platform · Weeks 3–10
Phase 2
Mobile apps & more · after Wk 10
Needed to move to build
Sign-off + advance
Domain, GCP, GSTIN
Meta verification, DLT
Razorpay KYC, Ads API
Price sheet + unit Excel
Photos & floor plans
WhatsApp number + wording
UAT feedback in 48 hrs
Sales team & roles
RERA data compilation
Renders, 360°, video, 3D
Ad accounts + UAT sign-off
Final app feature list
Play / App Store accounts
Store icons & screenshots
Delivery
Frozen scope & backlog
Architecture + repo
Staging on GCP
Design tokens
3D & RERA data test
Live website
OTP login + paid access
WhatsApp OTP & alerts
Admin: users, roles, uploads
Leads + pre-sales view
Pipeline, visits, holds
Reports, refunds, GST
Interactive 3D city map
360°, video, 3D viewers
Ads: spend → bookings
Bookings, ledger, privacy
Android & iOS apps
Push notifications
Advisor mobile app
AI assistant
Hindi / Kannada
Third-party tools
at cost
GCP · Workspace · GitHub
DLT ≈ ₹6k one-time
Razorpay ≈ 2% / txn
WhatsApp BSP ₹2.5–3.5k/mo
Firebase OTP / SMS
GA4 + Meta Pixel (free)
Video hosting, geocoding
3D model / 360° ₹30–90k
RERA data vendor (opt.)
VAPT ₹50k–2L
Apple Developer $99/yr
Google Play $25 once
Push via Firebase (free)
Maintenance
Weekly status call
Risk & approvals log
Daily backups
Uptime + error alerts
Launch hypercare
Weekly releases
Monthly RERA refresh
Retainer to be Quoted
App store releases
OS version updates
Retainer to be Quoted
Commercials
1 developer + 1 product/project lead
Tech Development + Setup + PM Efforts
TBD
TBD
Phase 1 and Phase 2 (grey) are indicative — scope, timing and pricing firm up once Phase 0 is live.
Tech work = development · Setup & PM = product/project management and third-party account creation and setup · 40% at phase start, 60% on UAT · third-party costs at actuals
Notes: Columns are phases; rows are what is needed to start building, what is delivered, third-party tools at cost, maintenance, and commercials. Commercials split pure tech work from setup and project management. Team: one developer and one product/project lead. Phase 1 and 2 are indicative.